## Sheet1
Risk | Description | Probability of Occurrence | Damage | Risk Factor | Risk Mitigation | Person in Charge of Tracking
Time delay | Time delay with the tasks assigned to a person within one sprint | 9 | specific features not completed, since we prioritize properly, that's not going to happen |  | reducing number of features when not necessarily required | All
server´s problem | Server not working, long loading time and loosing data, little risk since we do not have a huge user-base | 2 | Problems in loading data or app |  | Testing the server early and choosing the better server | Georg
unreliable teamwork | members are not as familiar with the given techs (as required) | 7 | Loosing time because of reading docs |  | Doing meetings during the project and connecting all the members. | All
get bogged down in bugs | WebApp not running because of bugs we are not able to find | 9 | Not being able to complete the project |  | not using libraries that we are too unfamiliar with, using as little features as possible, but as many as necessary | All
changes to requirements | possible, if one technology is not working as expected | 5 | might cost money to use other technology, time consumption due to reading all the docs |  | Only naming the broader technolgies (Django, jQuery, …) not getting too much into details with the specific libraries one wants to use. Look out for open source software | All
Disagreement | arguing about techologies, planning, priority,… | 3 | loosing time |  | democracy | All
Sickness | someone is ill | 10 | Not able to finish the project |  | can't happen since we don't have a substitution for Coding, Rama doesn't have Coding experience | Georg
Project Complexity | Project is growing out of proportion | 2 | loss of time |  | won't happen since we already reduced our project complexity on 26th of April | All

## Sheet2
Who's doing what
Rama | Georg
JavaScript | Persönliche Erfahrungen in JavaScript (jQuery, Google Charts) durch frühere Tätigkeit
Chart.js | Python --> Erfahrung mit Pandas durch frühere Tätigkeit
Eingabeblock ( Textboxen,…)
PHP -> Rechnung von Daten, die der Benutzer eingegeben hat
PHP -> Daten aus der Datenbank in HTML über Tabelle dargestellt